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Work included
This Section covers: Obtaining of all permits; moving onto the site furnishing and erecting temporary buildings, and other construction facilities; and implementing security requirements; all as required for the proper performance and completion of the Work. This Section also includes demobilization of all personnel and construction equipment.
The limits of the Owner's property or temporary easements designated for the Contractor's temporary facilities are shown on the Plans.
In the event additional space is required for the Contractor’s operations, the Contractor shall make their own arrangements and pay all costs related to the utilization of such additional space.
Mobilization shall include the following principal items:
Submittal and approval by the Engineer of the plans as outlined in Section 01 52 00 – Construction Facilities.
Moving on to the site.
Installing temporary construction power, wiring, and lighting facilities.
Establishing fire protection system.
Developing construction water supply.
Providing field and project office facilities for the Contractor and the Consultant, complete with all specified furnishings and utility services including telephone, telephone appurtenances, and copying machine. Install project signage (if applicable).
Providing all on-site communication facilities, including telephones, and Internet.
Providing on-site sanitary facilities and potable water facilities.
Arranging for and erection of work and storage yard.
Constructing and implementing security features and requirements complying with the General Conditions.
Obtaining all required permits.
Having all health and safety regulation required notices and establishment of safety programs.
Having the Contractor's superintendent at the job site full time.
Submitting initial submittals.
Negotiating any additional access easements deemed necessary to mobilize and complete the Work.
Demobilization shall include all activities and costs for transportation from the site of personnel, equipment, and supplies not required or included in the contract; including the disassembly, removal, and site cleanup of offices, buildings, and other facilities assembled on the site specifically for this contract.
This work includes mobilization and demobilization required by the contract at the time of award.  If additional mobilization and demobilization activities and costs are required during the performance of the contract as a result of changed, deleted, or added items of work for which the Contractor is entitled to an adjustment in contract price, compensation for such costs will be included in the price adjustment for the item or items of work changed or added.
Basis of payment
Payment shall be made as follows:
1. 60 percent of the lump sum price on the first Progress Payment.
40 percent of the lump sum price on the Completion Payment.
Products – Not used
Execution – Not used
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