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Quality Control Submittals: Submit certificates from inspecting authorities for electrical work, pressure piping, and gas piping among others.
[bookmark: _Toc41905558]Applicable codes and regulations
Comply with latest edition of the codes and standards referenced in Contract Documents and following statutes, regulations and codes, and all amendments thereto:
Building Code Act, 1992, S.O.1992, c. 23.
Building Code Act, Ontario Regulation (O. Reg) 332/12
CSA Certificate Standards
Canadian Environmental Protection Act (CEPA), S.C 1999, c. 33
Electricity Act, 1998, S.O. 1998, c. 15, Sched. A
Electricity Act, O. Reg 164/99 Electrical Safety Code
Environmental Protection Act (EPA), R.S.O. 1990, c. E.19.
EPA, O. Reg 101/94 Recycling and Composting of Municipal Waste
EPA, O. Reg 103/94 Industrial, Commercial and Institutional Source Separation Programs
EPA, O. Reg 102/04 Waste Audits and Waste Reduction Work Plans 
EPA, O. Reg 103/94 Industrial, Commercial and Institutional Source Separation Programs
EPA, O. Reg 406/19 On-Site and Excess Soil Management
EPA, O. Reg 419/05 Air Pollution – Local Air Quality
EPA, Regulation 347 General Waste Management
Environmental Noise Guideline, NPC-300, 2013
Ministry of Labour, Immigration, Training and Skills Development, Workplace Health and Safety resources 
National Building Code of Canada, 2020.
National Fire Protection Association (NFPA) Codes and Standards
Occupational Health and Safety Act (OHSA), R.S.O. 1990, c. O.1.
OHSA, O. Reg 213/91 Construction Projects
OHSA, O. Reg 632/05 Confined Spaces
Ontario Electrical Safety Code (OESC) Part 1, 2024, c. 22.1
Ontario Water Resources Act (OWRA), R.S.O. 1990, c. O.40.
OWRA, Regulation 903 (Wells), R.R.O. 1990
Technical Standards and Safety Act, 2000, S.O. 2000 c. 16 
Technical Standards and Safety Act, O. Reg 220/01 Boilers and Pressure Vessels
For purposes of the Occupational Health and Safety Act, the Contractor will be designated the “constructor” and assumes the responsibility of the constructor as set out in the Act and its regulations.
Submit the information required under Part I of O. Reg 213/91 to the Ministry of Labour, Immigration, Training and Skills Development prior to commencing work.
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Owner has obtained and paid only for the following permits and approvals:
1. Ministry of Environment, Conservation and Parks (MECP) Environmental Compliance Approval (ECA).
Municipality
Site Plan
Building Permit
Electrical Safety Authority (ESA)
Conservation Authority
Ministry of Natural Resources (MNR)
A copy of each approval or permit will be available upon award at the Owner's office for review upon request. Contractor shall examine the approvals and permits and conform to the requirements contained therein. Contractor shall confer with an agent of the permitting agency at an appropriate time so that any required arrangements will be in place prior to the time set for that portion of the Work.
Apply for, obtain, and pay for all other permits, approvals, and licences required for the project, including but not limited to:
1. Plumbing permit.
Canadian Gas Association (CGA).
ESA
Operating engineers.
Technical Standards and Safety Authority (TSSA).
Ontario Electrical Safety Code.
Pre-engineered Building.
Hydro One.
Bell Canada.
Owner will provide Contractor with a clean set of Contract Drawings and Specifications, as necessary, for each application.
Where electrical enclosures or panels require a field evaluation be responsible for such electrical enclosures or panels to be inspected and approved by the provincial electrical safety authority.
Arrange for regular inspections and a final inspection with:
1. ESA
Applicable branches of the TSSA
CGA
Plumbing Inspector.
Building Inspector.
HVAC Inspector.
Arrange for all other regular inspections and final inspections required.
The Contractor shall be solely responsible, without limitations, for any delays arising from the Contractor’s failure to plan for the required inspections and to ascertain the availability of the Permit/Approval/Licensing Inspectors to complete the required inspections for the Works under this Contract. The related costs and expenses incurred by the Contractor shall be borne by the Contractor, with no change in the Contract Price and/or Contract Time.
Ministry of Tourism, Culture and Gaming and Ministry of Sport Requirements
An Archaeological Assessment has been conducted for the site by a licensed archaeologist. No historic archaeological sites were discovered, and no archaeological remains were recovered during mitigative excavation.
It is possible that unexpected discoveries of deeply buried archaeological remains or human burials may occur during construction. If archaeological discoveries are found within the contract limits, the Contractor shall:
1. Cease grading and other activities that may result in the destruction or disturbance of any archaeological finds.
If the finds are deeply buried archaeological remains, immediately notify the Ministry of Tourism, Culture and Gaming and Ministry of Sport, the Owner and the Consultant.
If the finds are human remains, immediately notify the coroner, the police, the Owner and the Consultant.
Where practical continue the Work in other areas without interruption.
Protect finds as directed by the Consultant.
Removal of finds:
1. All finds are property of Owner. Do not remove or disturb finds without Owner’s written authorization.
Should Owner elect to have a find removed, provide equipment, labour, and material to permit safe removal of find without damage. Provide transportation for delivery to individuals, institutions, or other places as Owner may find desirable, expedient, or required by law. The cost of removing such finds will be paid for by the Owner.
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